## Sheet1
Task ID | Task Name | Duration | Start | Finish | Status | Predecessors | Resources | Deliverable
1 | SSD - Implementation of the SSD team project | 77 Days | 2022-03-08 | 2022-05-23
2 | Stage 1 - Design Document (20% of total module mark) | 43 Days | 2022-03-08 | 2022-04-18
3 | Team Formation | 3 Days | 2022-03-08 | 2022-03-11 | Completed
4 | Team Contract | 3 Days | 2022-03-11 | 2022-03-13 | Current Stage |  |  | Team Contract
5 | Suggested Domains Study | 3 Days | 2022-03-14 | 2022-03-16
6 | Preparation of draft bulleted list of system requirements and assumptions, design decisions and approaches | 3 Days | 2022-03-17 | 2022-03-20 |  | 5 |  | Draft bulleted list of system requirements and assumptions, design decisions and approaches
7 | Bulleted list of system requirements and assumptions, design decisions and approaches fune-tune & finailize | 2 Days | 2022-03-21 | 2022-03-22 |  | 6 |  | Bulleted list of system requirements and assumptions, design decisions and approaches
8 | Preparation of draft bulleted list of security risks/ vulnerabilities | 3 Days | 2022-03-23 | 2022-03-25 |  | 5 |  | Draft bulleted list of security risks/ vulnerabilities
9 | Bulleted list of security risks/ vulnerabilitiess fune-tune & finailize | 2 Days | 2022-03-26 | 2022-03-27 |  | 8 |  | Bulleted list of security risks/ vulnerabilities
10 | Preparation of UML design of solution with references | 4 Days | 2022-03-28 | 2022-03-31 |  | 5, 7, 9 |  | UML design of solution 1) Draft of the Class Diagram 2) Draft of the Sequence Diagram 3) Draft of the Activity Diagram
11 | UML design of solution with references fine-tune & finaialize | 2 Days | 2022-04-01 | 2022-04-02 |  | 10 |  | UML design of solution 1) The Class Diagram 2) The Sequence Diagram 3) The Activity Diagram
12 | Preparation of draft of bulleted list of tools (including development and test tools), libraries and models | 3 Days | 2022-04-03 | 2022-04-05 |  | 7, 9 |  | Draft of bulleted list of tools (including development and test tools), libraries and models
13 | Bulleted list of tools (including development and test tools), libraries and models fine-tune & finailize | 1 Day | 2022-04-06 | 2022-04-06 |  | 12 |  | Bulleted list of tools (including development and test tools), libraries and models
14 | Preparation of outline of the Design Proposal Report | 2 Days | 2022-04-07 | 2022-04-08 |  | 7, 9, 11, 13 |  | Draft of the outline of Design Proposal Report
15 | Submit the outline of Design Proposal Report for tutor's reviews and approval | 1 Day | 2022-04-09 | 2022-04-09 |  | 14
16 | The outline of Design Proposal Report fine-tune & finialize | 1 Day | 2022-04-10 | 2022-04-10 |  | 15 |  | The outline of Design Proposal Report
17 | Preparation of draft of the Design Proposal Report | 6 Days | 2022-04-11 | 2022-04-16 |  | 7, 9, 11, 13, 16 |  | Draft of the Design Proposal Report
18 | The Design Proposal Report fine-tune & finailze | 2 Days | 2022-04-17 | 2022-04-18 |  | 17 |  | The Design Proposal Report
19 | Stage 2 - Coding Output (40% of total module mark) | 34 Days | 2022-04-19 | 2022-05-23
20 | System Implementation | 14 Days | 2022-04-19 | 2022-05-02 |  | 18
21 | Preparation of Unit Test Cases | 1 Day | 2022-05-03 | 2022-05-03 |  | 18 |  | Unit Test Scripts
22 | Exercise Unit Test Cases | 1 Day | 2022-05-04 | 2022-05-04 |  | 20, 21 |  | Unit Test Results
23 | System fine-tune Round 1 | 2 Days | 2022-05-05 | 2022-05-06 |  | 22
24 | Prepartion of System Integration Test Cases | 1 Day | 2022-05-07 | 2022-05-07 |  | 18 |  | System Integration Test Scripts
25 | Exercise System Integration Test Cases | 1 Day | 2022-05-08 | 2022-05-08 |  | 23, 24 |  | System Integration Test Results
26 | System fine-tune Round 2 | 2 Days | 2022-05-09 | 2022-05-10 |  | 25
27 | Prepartion of Functional Test Cases | 1 Day | 2022-05-11 | 2022-05-11 |  | 18 |  | Functional Test Scripts
28 | Exercise Functional Test Cases | 1 Day | 2022-05-12 | 2022-05-12 |  | 26, 27 |  | Functional Test Results
29 | System fine-tune Round 3 | 2 Days | 2022-05-13 | 2022-05-14 |  | 28
30 | Prepartion of Load Test & Stress Test Cases | 1 Day | 2022-05-15 | 2022-05-15 |  | 18 |  | Load Test & Stress Test Scripts
31 | Exercise Load Test & Stress Test Cases | 1 Day | 2022-05-16 | 2022-05-16 |  | 29, 30 |  | Load Test & Stress Test Results
32 | System fine-tune Round 4 | 2 Days | 2022-05-17 | 2022-05-18 |  | 31
33 | Preparation of draft of the README file | 3 Days | 2022-05-19 | 2022-05-21 |  | 32 |  | Draft of the README file
34 | The README file fine-tune & finialize | 2 Days | 2022-05-22 | 2022-05-23 |  | 33 |  | The README file